NYOTA TECH

Software & Systems

Proposal & Quotation

WhatsApp Business API Integration

Prepared for: [Client Name]

Date: 23 May 2026

Reference: NT-Q-2026-001

Nyota Tech Limited

nyotatech.info@gmail.com

Table of Contents

1.  Executive Summary

2.  Technical Solution Overview

3.  Scope of Work

4.  Pricing & Fees

5.  Payment Terms

6.  Timeline

7.  Client Responsibilities

8.  Terms & Conditions

1.  Executive Summary

This proposal outlines an integration of Meta's official WhatsApp Cloud API into [Client]'s website, enabling the site to send WhatsApp messages to three designated mobile numbers programmatically — triggered by user form input.

The solution uses the WhatsApp Cloud API hosted by Meta (no on-premise infrastructure). A lightweight backend receives website form submissions and dispatches messages to each of the three recipients via approved message templates. All communications comply with WhatsApp's platform policies, including business verification, template approvals, and user opt-in consent requirements.

Target recipient numbers:

+260 977 161 191

+260 770 097 348

+260 973 971 192

2.  Technical Solution Overview

Architecture

Website Form  —  A user fills in a web form on [Client]'s site and submits it.

Backend Receiver  —  The form data is sent to a lightweight backend endpoint (Node.js / Python).

WhatsApp Cloud API  —  The backend calls Meta's Graph API (POST /messages) three times — once per recipient.

Message Delivery  —  Each recipient receives a WhatsApp message via a pre-approved template with personalised content.

Key Technical Details

API Endpoint: POST https://graph.facebook.com/v25.0/{Phone-Number-ID}/messages

Authentication: Permanent system-user token (no 24-hour expiry)

Message types supported: Text, template, media, interactive

Template categories: Utility (updates) and Marketing (promotions)

Meta infrastructure: Fully hosted — no servers, Docker, or on-premise maintenance

Platform Policy Compliance

Business verification via Meta Business Manager (company documentation required)

Pre-approved message templates for all business-initiated outbound messages

Explicit opt-in consent from each recipient before sending (auditable record)

24-hour customer-service window for free-form follow-up replies

3.  Scope of Work

Phase 1 — Setup (one-time)

Meta Business Manager account setup and configuration

Business verification submission and follow-through with Meta

WhatsApp Business Account (WABA) creation

Dedicated phone number registration and display name approval

Message template creation (1 Utility + 1 Marketing template) + Meta approval

User opt-in consent mechanism (web checkbox + record-keeping)

Backend integration — web form capture → API dispatch to 3 numbers

End-to-end testing with all three recipient numbers

Handover documentation and runbook

Phase 2 — Maintenance (monthly recurring)

Serverless / cloud hosting and uptime monitoring

WhatsApp template management and renewal as needed

Token and credential rotation (security best practice)

Ongoing technical support (48-hour first-response target)

Monthly delivery report

4.  Pricing & Fees

One-Time Setup Fee

| Item | Detail | Amount (USD) |
| --- | --- | --- |
| Base setup per number | 3 numbers × $100 each | $300.00 |
| Project margin | Project management, comms, buffer | $75.00 |
| Total One-Time Setup |  | $375.00 |

Monthly Maintenance Fee

| Item | Detail | Amount (USD) |
| --- | --- | --- |
| Hosting & infrastructure | Serverless / cloud hosting | $20.00 |
| Monitoring & support | 48h first-response, template mgmt | $10.00 |
| Total Monthly |  | $30.00 |

Meta Channel Costs (pass-through, variable)

| Category | Rate per message (+260) | Billing |
| --- | --- | --- |
| Utility (updates, alerts) | ~$0.0040 | Billed at cost + 5% admin |
| Marketing (promotions) | ~$0.0225 | Billed at cost + 5% admin |
| Authentication (OTP) | ~$0.0040 | Billed at cost + 5% admin |
| Service (inbound replies) | Free | Included |

5.  Payment Terms

50% of the one-time setup fee due upon signed agreement.

50% balance due upon completion, testing, and client acceptance.

Monthly maintenance invoiced at the start of each calendar month.

Meta channel costs billed monthly at cost plus a 5% administrative fee.

Payment is due within 14 days of invoice date.

All prices quoted in United States Dollars (USD).

6.  Timeline

Estimated duration: 2–3 weeks from signed agreement.

| Phase | Activity | Days |
| --- | --- | --- |
| 1 | Meta Business setup & verification submission | 1–3 |
| 2 | Meta verification processing (outside our control) | 3–14 |
| 3 | Template creation & approval (parallel) | 1–3 |
| 4 | Backend integration & API wiring | 3–7 |
| 5 | End-to-end testing with 3 numbers | 3–5 |
| 6 | Go-live & handover | 1–2 |

7.  Client Responsibilities

Provide company registration documents for Meta business verification.

Provide a dedicated phone number (not registered on personal WhatsApp).

Ensure opt-in consent is obtained from all three recipient numbers.

Review and approve message template content for Meta submission.

Provide website backend access or coordinate with the existing web developer.

Designate a single point of contact for the duration of the engagement.

8.  Terms & Conditions

This quotation is valid for 30 days from the date of issue.

Meta's business verification timeline is outside the control of Nyota Tech and may affect the overall delivery schedule.

All source code and configuration developed specifically for this project becomes the intellectual property of the client upon full payment.

Nyota Tech is not liable for WhatsApp platform policy changes, account suspensions, or service interruptions caused by Meta.

Any additional feature requests beyond the scope defined in Section 3 will be quoted separately.

Either party may terminate the monthly maintenance agreement with 30 days written notice.

Nyota Tech Limited  |  nyotatech.info@gmail.com

Calm, dependable software.